ANNEX 5, APPENDIX 1: PROCEDURE FOR AMENDMENT OF THE CONTRACT

MINOR CHANGES – NOTIFICATION LETTER:

Preparation of Notification Letter

Minor change in the Contract is communicated with CFCU through Notification Letter. The following are the steps how to prepare and submit Notification Letter:

- Prior consult the need for modification with the responsible Grant Coordinator and the Contract Manager in the CFCU

- Prepare the notification letter following the standard forms in English

- Any notification modifying the budget must include a “revised budget” showing how the budget breakdown of the initial contract, and any previous changes, if any, has been modified by this change.

- CFCU notifies the Grant Beneficiary accordingly about the acceptance or rejection of the request.

- Additional documents that have to be attached to the notification letters together with the justifications are as follows:

| Increase of approved salaries/fee rates | Document proving that new requested salaries do not exceed those normally borne by the Beneficiary or his partners |
| --- | --- |
| Increase of approved unit rates or number of equipment | Document proving that the new requested rates do not exceed normal market rates |
| Change of auditor | Registration certificate of the chamber of auditors |
| Change of expert | CV of the initial and new(proposed) expert |
| Modifications in budget | “Budget for the Action” showing how the budget breakdown of the initial contract, and any previous changes, if any. |
| Change in Activities/Action Plan | Revised Action Plan. |

MAJOR CHANGES – ADDENDUM:

- The justification for grant addendum is consulted with the responsible Contract Manager in the CFCU and Grant beneficiary prior to official submission.

- Grant beneficiary prepares Request of Addendum using the standard template (Letter- Addendum request letter) and submits to the CFCU and copy to the JTS min 30 days before the change should enter into force

Any addendum modifying the budget must include a “modification budget” showing how the budget breakdown of the initial contract, and any previous changes, if any, has been modified by this addendum.

- Contract Manager in the CFCU reviews the original request of the Grant Beneficiary.

- CFCU will review if addendum is feasible drafts Explanatory note, using standard template and any revised annexes (if applicable). Prepares three originals of the proposed addendums. Upon internal approval within the CFCU and ex-ante approval by the EUD the addendum is submitted to the Coordinator for counter signature.

- If addendum is not feasible letter will be sent to the Grant Beneficiary.

- Annex 5, Appendix 2: Budget notification example

- Annex 5, Appendix 3: Explanatory note

- Annex 5, Appendix 4: Template - Excel Sheet for Re-allocation

- Annex 5, Appendix 6: Template for Notification Letter

- Annex 5, Appendix 5: Template for request for addendum