# B.	DRAFT CONTRACT AND SPECIAL CONDITIONS, INCLUDING ANNEXES

# DRAFT CONTRACT

SUPPLY CONTRACT FOR EUROPEAN

UNION EXTERNAL ACTIONS

No <Contract number>

financed from the general budget of the Union

The Government of the Republic of Serbia, represented by the Ministry of Finance, Department for Contracting and Financing of EU Funded Programmes (CFCU), 3-5 Sremska St, 11 000 Belgrade

(‘The contracting authority’),

of the one part,

and

<Full official name of contractor>

[<Legal status/title>]

[<Official registration number>]

<Full official address>

[<VAT number>], (‘the contractor’)

of the other part,

have agreed as follows:

- CONTRACT TITLE

- Equipping Preschool Institutions

- Identification number EuropeAid/139409/IH/SUP/RS

- Article 1	Subject

1.1	The subject of the contract shall be the supply, delivery, unloading, installation, testing and commercial warranty by the contractor, of the following supplies:

| LOT 1: Furniture and Equipment |  |  |
| --- | --- | --- |
| Item | Description | Quantity |
| 1 | Double sided shelf | 793 |
| 2 | Shelf for science centre | 793 |
| 3 | Mobile shelf for art centre | 793 |
| 4 | Movable low shelf with light - for research activities with light or magnet, for creative painting with sand and similar materials under light and other research | 793 |
| 5 | Nap Cot | 11.680 |
| 6 | Wallboard (white or green) for writing with pens or chalk | 793 |
| Training | No specific training is foreseen for the items stated in this Lot, except for the basic introduction to the items. |  |

The place of acceptance of the supplies shall be at the addresses specified in the Distribution list - Lot 1 (Attachment to the Annex II +III Technical specifications + Technical Offer), the time limits for delivery shall be 210 days and the Incoterm applicable shall be DDP. The implementation period of tasks shall run 365 days from the day of issuance of Commencement Order to the day of issuance of the certificate of Provisional Acceptance.

1.2	The contractor shall comply strictly with the terms of the special conditions and the technical annex.

- Article 2	Origin

The rules of origin of the goods are defined in Article 10 of the special conditions.

A certificate of origin for the goods must be provided by the contractor at the latest when it requests provisional acceptance of the goods. Failure to comply with this condition may result in the termination of the contract and/or suspension of payment.

- Article 3	Price

3.1	The price of the supplies shall be that shown on the financial offer (specimen in Annex IV). The total maximum contract price shall be EUR <insert price>

3.2 	Payments shall be made in accordance with the general and/or special conditions (Articles 26 to 28).

- Article 4	Order of precedence of contract documents

The contract is made up of the following documents, in order of precedence:

- the contract agreement;

- the special conditions

- the general conditions (Annex I);

- the technical specifications (Annex II including clarifications before the deadline for submission of tenders);

- the technical offer (Annex III including clarifications from the tenderer provided during tender evaluation);

- the budget breakdown (Annex IV);

- specified forms and other relevant documents (Annex V);

- The various documents making up the contract shall be deemed to be mutually explanatory; in cases of ambiguity or divergence, they shall prevail in the order in which they appear above.

Done in English in three originals, one original being for the contracting authority, one original being for the EU Delegation, and one original being for the contractor.

| For the contractor |  | For the contracting authority |  |  |
| --- | --- | --- | --- | --- |
| Name: |  | Name: |  |  |
| Title: |  | Title: |  |  |
| Signature: |  | Signature: |  |  |
| Date: |  | Date: |  |  |

Where the contracting party is an individual.

Where applicable. For individuals, mention their ID card or passport or equivalent document – number.

Except where the contracting party is not VAT registered.

DDP (Delivered Duty Paid)- Incoterms 2010 International Chamber of Commerce - http://www.iccwbo.org/incoterms/